- Event Plan Development – Project Initiation

  - Budget

    - Confirm budget amount

  - Historic information Review

    - Learning’s from previous events

  - Meeting Brief

    - Situation Analysis

      - Leadership Business Objectives

      - Voice of Customer – Audience needs

    - Brief or Scope

      - Define audience

      - Goals

      - Purpose

      - Measurable Objectives

      - Theme & Structure

      - Timing

      - Event Elements

        - Element Briefs as needed

          - Receptions

          - Sessions

          - Brand Rooms

          - Trade Shows

          - Awards Dinner

          - Sales Meetings

          - Other

      - Venue & Set

      - Preliminary Running Order

      - Speaker Decisions

      - Preliminary schedule

      - Project costs & benefits

    - Steering Team Approval

      - Communicate proposed dates with Leadership

      - Meeting Brief completed and signed off by Leadership

      - Meeting Brief submitted for review

      - Meeting Brief:  Sell in to Sr. Team

  - Roles, Responsibilities

    - Roles & Responsibilities

      - R & R Identified

      - R & R definitions finalized

      - Approve R & R document

      - Distribute R & R document

    - Teams

      - Identify Teams

        - Production

        - Communications

        - Logistics

        - Transportation

        - Hospitality & Catering

        - Brand Teams

        - Budget

  - Productivity Tools

    - Extranet

      - Site folders set-up,

      - Send communication to planning team

      - Training as needed

    - Review standards/templates

      - Formats

      - Standard documents

  - Venue/Site Selection

      - Preliminary venue/site selection

      - Venue/Site visit

        - Event elements vs. space consideration

        - Audience size and demographics

      - Comparison of sites

      - Site selected

      - Contract developed

- Event Development – Project Planning

  - Roles, Responsibilities, Staffing

    - Staffing & Resource Identification

      - Identify scope, resource needs from suppliers

        - Internal

        - M & E Resource team

        - External

          - Determine RFP requirements as needed

            - Production Company

            - Display company

            - Talent

            - Hospitality

            - Etc.

      - Contact

      - Budget

      - Approve

      - Contract

      - P.O.

    - Team Assignments via R & R documents

    - Contact List

      - Develop

      - Approve

      - Distribute

  - Budget

    - Development begins

    - Budget reviewed by element

    - Budget(s) approved

  - Planning Process & Training Tools

    - Planning Meetings

      - Determine Meeting Schedule

      - Attendees

      - Agenda

      - Desired Results

      - Communication tools

      - Action Items - Set Up, Drive & Track

      - Issues - Set Up, Drive Resolution & Closure

      - Minutes

    - Event Bible/Encyclopedia (One-stop source for event information)

        - Determine owner

        - Determine template

        - Determine process for assembly

  - Facility Utilization

    - Site survey – functional

    - Space grid developed

    - Space assigned

    - Ancillary meetings noted

  - F&B

    - Menus

    - Locations

    - Costing

    - Layout/schematic

    - Tables/chairs

    - Specification

  - Environment (Décor)

    - Linens

    - Centerpieces

    - Floral

    - Décor

    - Lighting

    - Audio

    - Scenery

  - Beer Order

    - Determine Distributor contact

    - Develop beer order

    - Beer handling process

  - Local Market Relationship

    - Distributor contact

    - Sales Region contact

    - Local market needs

  - Transportation

    - Group

    - Air

    - Information

    - VIP

  - Sleeping Rooms

    - Attendee

    - VIP assignments

    - Staff

    - Review room pick-up to date (multiple reviews)

    - Reservation deadline

    - Attrition

  - Space Management

    - Event Spaces

      - Executive Offices

      - Production Office

      - Off-line

      - General Session

      - Brand Showcase

      - Reception

      - Security

      - Green Room

      - Ancillary Meetings

      - Other

    - Plan developed

    - Plan approved

    - Review supplies

    - Space infrastructure needs

      - Furniture

      - Communications

      - Equipment

    - Materials ordered

    - Staffing schedule

  - Shipping and Freight

    - Determine needs

    - Determine methodology

    - Define schedule

    - Deploy shipping instructions

    - Drayage

    - Storage

    - Bone-yard

  - Safety & Security

    - Develop risk/safety plan

      - Establish relationship with local law enforcement

      - Fire Marshall

      - Requirements

      - Resources

    - Security Personnel

    - Technologies

      - Radios/Cells Phones/Other Hand Helds

    - Security Process for Attendees

      - Registration & Check-in

      - Badges & Identification

      - Authorized list of 'All Access' badges

      - Badges to production crew(s)

    - Emergency Resources (EMTs/Ambulance)

  - Attendee Management

    - Criteria

      - Develop

      - Approve w/ - Leadership

    - Develop Lists

      - Customer Attendees

      - Employee Attendees

      - VIP attendees

      - Presenters

      - Staff Attendees

      - Agencies/Guests

      - Press

      - Award Winners

    - Attendee Communication

      - Hold the date

      - Registration process and website

      - Website Registration Begins

      - Draft "Know Before You Go" document

      - Send "Know Before You Go"

    - Manage Attendees

        - Gather names / emails of attendees

        - Contact as needed,

          - Identify personal needs

          - Identify information / documents needed

        - Transportation arrangements as needed

        - Security arrangements as needed

        - Arrange escort as needed

        - Confirm presenters schedule as needed

        - Send transportation schedule and details as needed

        - Arrange escort as needed

        - Arrival/departure schedule

  - Collateral

    - Needs identified

      - Badges

        - Badge–holder

        - Inserts

        - Special needs

          - Access specific

          - VIP

      - Signage

      - Way-finding

      - Agenda

      - Other

    - Design

      - Theme development

      - Design needs to artist

      - Approve layouts

    - Content

      - Content development

      - Copy approval

    - Proofs reviewed

    - Elements to print

    - Registration materials ordered

    - Registration material assembled

    - Ship materials

  - Amenities

    - Needs identified

    - Theme development

    - Design needs to artist

    - Approve layouts

    - Ordered

    - Produced

    - Assembled

    - Ship materials

  - Awards

    - Identify awardees

    - Identify awards

  - Registration

    - Event

      - Website

        - Web registration site development

        - Website copy and functionality developed

        - Website testing

        - Website active

        - Reports generated

      - On-site Registration Desk

        - Design

        - Materials

        - Hours

        - Staffing

    - Hotel

      - Web room reservation

        - Link from event Website

        - Testing and Functionality

      - On-site Room Check-in

        - Flow

        - Staffing

  - Post-event Communications

    - Attendee Survey

      - Question development

      - Approval

    - Event Take-aways

    - Postings

      - Intranet

      - Extranet

  - Press

    - Send invitation to press

    - Schedule interviews

    - Write release

    - Approve release

  - Content & Delivery Preparation – i.e General Session, Meeting, Award Events, Brand Experience

    - Event “Spoken” Content

    - Spoken Presentation (General Session, etc.)

      - Confirm "key dates" on presenters calendars

      - Briefs

      - Outlines

      - Outlines to Presenter

      - Draft 1 to Presenters

      - Identify video needs, develop production schedule

      - Draft 2 to presenters

      - Final Draft to presenters

      - To visualization

      - Script books assembled / distributed for read thru

    - Interactive Brand Experience

      - Brand feature decision

      - Experiences

        - Brands with live experience areas

        - Brands that have presence but not 'brand area'

      - Experiences/content development

    - Award Events

      - Presentations

      - Awards

    - Event “Visual” Content

    - Graphic/visual support development

      - Develop graphic templates

      - Graphics templates approved

      - Visualization of presentations

      - Graphics review(s)

    - Video Elements development

      - Support Video

        - Identify video needs, develop production schedule

        - Hire production

        - Produce

        - Approve

      - Commercials/Advertising

        - Determine commercials to be shown

        - Coordination with agency – specifications, dates, etc

        - Receive elements

      - Show reel

        - Develop list

        - Receive elements

        - Create reel

        - Approve reel

    - Outside Presenters/Entertainment

      - Needs determined

      - Options reviewed

      - Budget reviewed

      - Rider considered

      - Presenter selected

  - Content & Delivery - Review & Practice

    - Read-thru & approval

      - Location

      - Schedule

      - Books

        - # Book

        - Tabs

    - Presenter Practice & Rehearsals

      - Teleprompter rehearsal

      - Visual synchronization

      - Coaching

      - Technical rehearsal

      - Dress rehearsal

    - Show Books

      - Final prompter script

      - Final graphic printouts

      - Miscellaneous notes

      - Deliver command and control to technical producer

  - Staging & Production

    - Production schedule developed

    - Set Design & Approval

    - Production Design & approval

      - Floor plan

      - Lighting plan

      - Audio Plan

      - Video Plan

      - Graphics Plan

      - Teleprompter placement

      - Crew selection & approval

      - Layouts/ Mockups

    - Special Considerations

      - Brand Experience

      - Award Events

      - General Sessions

      - Trade Shows

      - Etc.

- Event On-site Execution – Executing

  - Load-in

    - Event Elements - Where attendees go (GS, Reception, Interactive Brand showcase, Registration)

      - Facilities

      - Labor & Union

      - Equipment

    - Logistics – What supports attendees (office, back of house functions)

      - Facilities

      - Labor Schedule

      - Equipment

  - Rehearsals

    - Offline

    - Technical

    - Walk-thru

    - Dress

    - Final element assembly (graphics, videos, content)

  - Content Delivery – Final

    - Content books to tech producer

    - Video reel delivered to tech producer

  - Event Element Execution

    - Registration

    - Reception

    - General Session

    - Ancillary Meetings

    - Press interviews

    - Off-sites

    - Brand Event

    - Employee Meeting

    - Sales & marketing Award

  - Load-out

    - Labor schedule

    - Equipment

    - Union considerations

- Post-event – Monitor, Control & Close

  - Communications

    - Attendee Survey

      - Distribution

      - Analysis

      - Report

      - Determine ROI

    - Take Aways

    - Postings

  - Production teams debrief

    - Post-mortem

    - Lessons learned

  - Budgeting & Billing

    - Pay bills

    - Reconcile Budget vs. actual

  - Freight

    - Return

    - Re-stock

  - Content

    - Document

    - Library