## Notes on Worksheet
1 | Example is based on starting in April in one year and the conference being held in mid October the following year.
2 | Not all tasks shown may be relevant for any particular conference and there may be tasks relevant to your own environment that are not included in this example.
3 | The sequence of tasks is a guide only and some tasks are dependent on others being completed beforehand.
4 | The sequence of tasks may vary depending on your own requirements and timing (such as end of financial year) will effect when tasks should be done.
5 | Should your own planning period be shorter, it may be possible to use less columns and by making them wider, you could include the actual date (DD/MMM) in the columns F through to Z or simply insert the day number DD.
6 | The Resp. Column (D) should have the initials of the Person Responsible. If a task is shared between two people, one must have the responsibility.
7 | The Month Column (E) should have actual dates (DD/MMM) so the Worksheet can be sorted by date.
8 | The Excel Sort feature can be used to group tasks by Person, Date or Category
9 | Additional comments can be included by using the Excel Comment feature and can be "hidden" until you place the mouse pointer over that cell. In this example, the comments have been made to show all the time. Refer Cell B1 in the Example Timeline.
10 | The Comments can be made to print or to not print. Refer to Page Set Up, Sheet & Comments.
11 | Note that data in some Cells has been "hidden" by using a white font.
12 | By estimating the hours involved in all the conference tasks, you can determine the total hours for the project. Ensure you are conservative. You may then cost the total hours by your average hourly rate to see what the project should cost.
13 | If you are using a PCO (Professional Conference Organiser), you will still have to do many tasks yourself. Do not underestimate the impact that organising a conference will have on your own time and your own staff.
Note on B9: Comment feature allows Comments to be visible at all times or only displayed when the pointer is placed on that cell.
Note on B12: As a guide, you could expect a 300 person, three day, 20 exhibitor, 60 presenter conference to take 800 - 1000 hours to organise and manage.

## Example Timeline
1 | Comment | Key Dates then Tasks below / Months to the right | 1 | 1 | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | Comments
2 | 2 Key | Review meetings | 2 | 2 | [21 empty] | Check Committee availability | bar: A to D
3 | 3 Key | Select Venue |  | May | [21 empty] | ASAP to ensure you get the Venue on dates you prefer | bar: M
4 | 4 Key | Invited Presenters - Confirm | 4 | Aug | [21 empty] | Required for Call for Presenters | bar: A
5 | 5 Key | Call for Presenters - Distribute | 5 | Jan | [21 empty] | www site updated | bar: J
6 | 6 Key | Call for Presenters - Close off date | 6 | Feb | [21 empty] | Allow time to produce the draft program | bar: F
7 | 7 Key | Program - Finalised | 7 | Mar | [21 empty] | All Presenters & all topics | bar: M
8 | 8 Key | Registration Booklet - Mailed | 8 | May | [21 empty] | www site updated | bar: M
9 | 9 Key | Early bird discount rate closes | 9 | Jul | [21 empty] | Allow five to six weeks to mid rate | bar: J
10 | 10 Key | Mid discount rate closes & normal rate starts | 10 | Aug | [21 empty] | Allow minimum five weeks to conference | bar: A
11 | 11 Key | Conference (e.g. Mid Oct) | 11 | Oct | [21 empty] | DIY Conferences | bar: O
12 | Category | Tasks | Per. Resp. | 12
13 | M'gement | Committee - Form management committee & specific roles |  | Apr | [21 empty] | First task after deciding if event is feasible | bar: A
14 | M'gement | History - Obtain reports from previous conferences |  | Apr | [21 empty] | Statistics, regn Booklets, fees, highs & lows | bar: A
15 | Accom. | History - Research previous requirements & utilisation |  | Apr | [21 empty] | Accommodation range, numbers, rates | bar: A
16 | Finance | Budget - Obtain previous conference financial reports |  | Apr | [21 empty] | To assist with your own budget | bar: A
17 | Spon'ship. | History of previous Exhibitors - Obtain names |  | Apr | [21 empty] | Bookings, potentials | bar: A
18 | Spon'ship. | History of previous Exhibitions - Obtain Packages |  | Apr | [21 empty] | Prospectus, packages. floorplans, numbers booked | bar: A
19 | M'gement | Research - Conflicting events, other opportunities |  | Apr | [21 empty] | Decide on dates | bar: A
20 | M'gement | Goals - Planning workshop on goals, conference structure |  | Apr | [21 empty] | Major decision day on all aspects of the conference | bar: A
21 | M'gement | Brief - Send to selected Conference Organisers |  | May | [21 empty] | Size, structure, specific needs, tasks required | bar: M
22 | M'gement | Organisers - Review Proposals & meet potential Organisers |  | May | [21 empty] | Check references, synergy, management systems | bar: M
23 | M'gement | Contract - Finalise with Organiser |  | May | [21 empty] | Define responsibilities, variable costs | bar: M
24 | Educ. Prog. | Structure - Decide on daily format, sessions |  | May | [21 empty] | Reqd to decide on venue suitability | bar: M
25 | Venue | Venues - Research possibles & visit to determine suitability |  | May | [21 empty] | Program structure, exhibition size, affordability | bar: M
26 | M'gement | Dates - Decide on suitable conference dates |  | May | [21 empty] | Consider history, competition, holidays, local events | bar: M
27 | Venue | Brief - Prepare & send conference brief to selected Venues |  | May | [21 empty] | Send by mail or email | bar: M
28 | Venue | Receive proposals & evaluate venue |  | May | [21 empty] | Check liabilities, costs, surcharges, other bookings | bar: M
29 | Venue | Conference Rooms - Check heights, pillars, doors |  | May | [21 empty] | Check obstructions, Fire exits | bar: M
30 | Venue | Venue Contract - Review & Complete |  | May | [21 empty] | Involve Organiser | bar: M
31 | Venue | Conference structure - Decide on conference rooms required |  | May | [21 empty] | Days, capacities, exhibition space, accommodation reqd | bar: M
32 | Educ. Prog. | Call for Presenters - Decide how to be publicised & when |  | May | [21 empty] | Post, email, costs, quantities (if printed) | bar: M
33 | M'gement | Prepare Project Schedule of major tasks |  | Jun | [21 empty] | Key dates set at workshop | bar: J
34 | M'gement | Assign hours to each task |  | Jun | [21 empty] | Exercise to determine resources reqd and when reqd | bar: J
35 | M'gement | Software - Review how Event Software will be used |  | Jul | [21 empty] | How can you use the features? | bar: J
36 | Accom. | Venues - Research suitable hotels & visit |  | Jun | [21 empty] | Rates, styles, location, rooms available | bar: J
37 | Accom. | Contracts - Decide on room blocks, review dates, deposits |  | Jun | [21 empty] | Consider different levels of accommodation ratings | bar: J
38 | Finance | Registration Fees - Review history, set categories & fees |  | Jun | [21 empty] | Consider what market will accept | bar: J
39 | Finance | Bank Account - Arrange |  | Jul | [21 empty] | Signatories? | bar: J
40 | Finance | Bank Account - Arrange seed funding |  | Jul | [21 empty] | Amount to be repaid | bar: J
41 | Finance | Budget - Prepare draft & approve |  | Jun | [21 empty] | Budget review at each committee meeting or monthly | bar: J
42 | Finance | Prepare a cash flow forecast |  | Jun | [21 empty] | What expenses are payable before income begins | bar: J
43 | Printing | Theme, Logo - Decide for letterhead & promotion |  | Jun | [21 empty] | Letterhead for Presenters, sponsors, delegates | bar: J
44 | Promotion | Plan - Decide how event is to be promoted |  | Jul | [21 empty] | Mail, www site, inserts, newsletters, diary dates, media | bar: J
45 | Promotion | Journals & newsletters - Decide where adverts are useful |  | Jul | [21 empty] | What publications does the market read? | bar: J
46 | Promotion | Advertisements - Decide on content |  | Jul | [21 empty] | What, where, when, costs? | bar: J
47 | Promotion | Mailing lists - Research availability |  | Jul | [21 empty] | What data bases are appropriate, numbers & costs | bar: J
48 | Promotion | Mailing lists - Decide on ones to be used |  | Jul | [21 empty] | Check suitability | bar: J
49 | Promotion | www site - Decide on hosting |  | Jul | [21 empty] | Who, where, content, updates | bar: J
50 | Promotion | www site - Updates - Decide on content & dates |  | Jul | [21 empty] | Conference, Sponsorship, Registration, Program | bar: J
51 | Educ. Prog. | Structure - Prepare draft & approve |  | Jul | [21 empty] | Key sessions, concurrents, posters, exhibition, times | bar: J
52 | Educ. Prog. | Invited Presenters - Decide on entitlements |  | Jul | [21 empty] | Air & ground travel, accom, registration, partners | bar: J
53 | Educ. Prog. | Invited Presenters - Select & contact |  | Aug | [21 empty] | Check on availability, costs | bar: A
54 | Educ. Prog. | Presenters - Decide on entitlements |  | Aug | [21 empty] | Discounted registration or other | bar: A
55 | Educ. Prog. | Presenters - Approve Presenters Agreements |  | Aug | [21 empty] | Benefits, AV, papers, copyright, media | bar: A
56 | Educ. Prog. | Invited Presenters - Collect CV's, photos, topics |  | Aug | [21 empty] | May be reqd for first flier | bar: A
57 | Educ. Prog. | Invited VIP's, politicians - Decide who is suitable |  | Aug | [21 empty] | Collect photos, CV's, topics for first flier | bar: A
58 | Educ. Prog. | Educational tours - Research & decide upon |  | Aug | [21 empty] | Numbers, venues, times, transport | bar: A
59 | Educ. Prog. | Invited Presenters - Confirm entitlements |  | Aug | [21 empty] | Air fares, accommodation, fees, partners, other expenses | bar: A
60 | Educ. Prog. | Invited Presenters - Collect CV's, topics |  | Aug | [21 empty] | Collect photos, CV's, topics for first flier | bar: A
61 | Social Prog. | History - Review previous conferences social events |  | Aug | [21 empty] | What worked & what didn't? | bar: A
62 | Social Prog. | Research - Suitable social events |  | Aug | [21 empty] | What will attract people to the Venue or Destination | bar: A
63 | Social Prog. | Research - Social attractions, activities, tours |  | Aug | [21 empty] | Capacities, access, costs, transport, catering | bar: A
64 | Social Prog. | Accompanying persons’ program - Decide on format |  | Sep | [21 empty] | Depends on demographics of attendees & past history | bar: S
65 | Promotion | www site - Design draft format, content |  | Sep | [21 empty] | Required early for promotion, look for suitable links | bar: S
66 | Social Prog. | Structure - Prepare draft & approve |  | Sep | [21 empty] | Reqd. for Registration Book | bar: S
67 | Social Prog. | Venues - Book social Venues |  | Sep | bar: S
68 | Social Prog. | Descriptions & photos - Arrange |  | Sep | [21 empty] | Collect photos, costs, descriptions for publications | bar: S
69 | Spon'ship. | Sponsor fees - Research other conference fees |  | Sep | [21 empty] | History & other similar conferences sponsorship fees | bar: S
70 | Spon'ship. | Sponsorship invitation - Prepare |  | Sep | [21 empty] | Decide on costs & benefits for sponsors | bar: S
71 | Spon'ship. | Exhibition floorplan - Prepare draft of Layout |  | Sep | bar: S
72 | Spon'ship. | Exhibition floorplan - Review with Venue |  | Sep | [21 empty] | Consider OHS, fire exits, catering stations | bar: S
73 | Spon'ship. | Exhibition Contractor - Arrange quotes & review |  | Sep | [21 empty] | Familiarity with Venue, references | bar: S
74 | Spon'ship. | Exhibition Contractor - Select & sign contract |  | Oct | bar: O
75 | Spon'ship. | Exhibition floorplan - Review with Contractor |  | Oct | [21 empty] | Building time, access, pull down time | bar: O
76 | Transport | Travel Agency - Appoint |  | Oct | [21 empty] | May be required for First Flier & www site | bar: O
77 | Promotion | Previous Meeting - Attend to review success & Promotion |  | Oct | [21 empty] | Meet Committee, Sponsors, Exhibitors, Organisers | bar: O
78 | Promotion | Announcement - Design & print first flier |  | Oct | [21 empty] | Themes, key Presenters, topics, sponsors, days | bar: O
79 | Spon'ship. | Sponsor & exhibitor database - Compile |  | Oct | [21 empty] | who exhibited at previous conferences, who advertises? | bar: O
80 | Spon'ship. | Sponsorship invitation - Review with major sponsors |  | Oct | [21 empty] | Ensure that fees / benefits are suited to the market | bar: O
81 | Promotion | www site - Review & test |  | Oct | bar: O
82 | Promotion | www site - Implement |  | Oct | [21 empty] | Similar content to first flier | bar: O
83 | M'gement | Online Registration - Decide on process |  | Nov | [21 empty] | On-line verification of credit cards etc | bar: N
84 | M'gement | Registration Software - Set up |  | Nov | [21 empty] | Set up sessions, social, standard letters, registration options | bar: N
85 | Spon'ship. | Sponsorship invitation - Distribute |  | Nov | [21 empty] | Post, email - begin selling | bar: N
86 | Promotion | www site - Update with Exhibitor Invitation |  | Nov | bar: N
87 | Promotion | Announcement - Distribute |  | Nov | bar: N
88 | Aud'visual | Audiovisual - Decide on what will be available |  | Nov | [21 empty] | Costs, requirements | bar: N
89 | Aud'visual | Brief - Send brief to selected AV Companies |  | Nov | bar: N
90 | Aud'visual | Proposals - Review AV Proposals |  | Dec | bar: D
91 | Aud'visual | AV Supplier - Select & Book |  | Dec | bar: D
92 | Aud'visual | Review options, costs, feasibility |  | Dec | [21 empty] | Audience voting, www cast, overseas links | bar: D
93 | Educ. Prog. | Call for Presenters - Review print quantity |  | Dec | [21 empty] | Data bases to be used, inserts in journals | bar: D
94 | Educ. Prog. | Call for Presenters - Decide how to be submitted |  | Dec | [21 empty] | On-line or via email | bar: D
95 | Educ. Prog. | Call for Presenters - Decide how Abstracts to be reviewed |  | Dec | [21 empty] | Select Review panel | bar: D
96 | Educ. Prog. | Call for Presenters - Prepare draft & approve |  | Dec | [21 empty] | Date for receipt, process for submission, format required | bar: D
97 | Educ. Prog. | Call for Presenters - Design & Print |  | Jan | [21 empty] | Review quantity | bar: J
98 | Educ. Prog. | Call for Presenters - Distribute |  | Jan | [21 empty] | Post & email of first flier | bar: J
99 | Promotion | Advertisements - Decide on format |  | Jan | [21 empty] | Copy & design finalised | bar: J
100 | Promotion | Advertisements - Arrange |  | Jan | [21 empty] | Publications & when? | bar: J
101 | Educ. Prog. | Opening & Closing ceremonies - Decide on format |  | Jan | [21 empty] | Impact opening reqd & what will keep people for the close? | bar: J
102 | Spon'ship. | Status - Review success of invitation & sales |  | Feb | [21 empty] | Does Invitation need adjustment? | bar: F
103 | Social Prog. | Entertainment - For reception, dinners, opening, closing |  | Feb | [21 empty] | Availability, costs, requirements | bar: F
104 | Social Prog. | Themeing - Decide on format, requirements |  | Feb | [21 empty] | Production, lighting, costs | bar: F
105 | M'gement | Risk assessment - Review risks involved |  | Feb | [21 empty] | No shows, non insurable risks, medical, disruption | bar: F
106 | M'gement | Risk assessment - Form policy |  | Feb | [21 empty] | Plan incident reports, how each situation to be handled | bar: F
107 | Finance | Insurance - Arrange quotes, select & sign policy |  | Feb | [21 empty] | Prof Indemnity, disruption, forced cancellation, weather | bar: F
108 | Venue | Parking - Check availability, costs |  | Feb | [21 empty] | Delegates, VIP's, in house guests | bar: F
109 | Venue | Room Capacities - Review |  | Feb | [21 empty] | Check Numbers & Layouts | bar: F
110 | Educ. Prog. | Educational tours - Liaise with hosts |  | Feb | [21 empty] | Collect final detail for regn booklet | bar: F
111 | Educ. Prog. | Educational tours - Arrange bookings |  | Feb | [21 empty] | Contracts with hosts or venues | bar: F
112 | Educ. Prog. | Opening ceremony - Arrange |  | Mar | [21 empty] | Book Performers, entertainment, staging | bar: M
113 | Social Prog. | Entertainment - Book |  | Mar | [21 empty] | Check costs, insurance | bar: M
114 | Educ. Prog. | Abstracts - Receive & Collate |  | Mar | [21 empty] | Distribute to Committee for review | bar: M
115 | Educ. Prog. | Abstracts - Review & decide on Presenters |  | Mar | [21 empty] | Advise all who submitted abstracts | bar: M
116 | Promotion | Media - Collate contact list |  | Mar | [21 empty] | Mail, email, phone, interests | bar: M
117 | Promotion | Media - Prepare material to be distributed |  | Mar | [21 empty] | How, when | bar: M
118 | Printing | Registration Book - Prepare draft |  | Mar | [21 empty] | Collate all text, photos & layout ready for graphic design | bar: M
119 | Printing | Registration Book - Approve draft |  | Mar | [21 empty] | Also approve after design finalised | bar: M
120 | Printing | Registration Book - Design & print |  | Apr | [21 empty] | Ensure design is appropriate for www site as well | bar: A
121 | Printing | Registration Book - Distribute |  | May | [21 empty] | Post | bar: M
122 | Promotion | Internet registration facility - Arrange |  | May | [21 empty] | Program to allow data entry by delegate | bar: M
123 | Promotion | www site - Update with Registration Book |  | May | [21 empty] | Send www alert to data base | bar: M
124 | Educ. Prog. | Invited Presenters - Arrange Travel |  | Jun | [21 empty] | Booking, payment, cancellation | bar: J
125 | Accom. | Presenters, Committee & Staff - Book rooms |  | Jun | [21 empty] | Advise regarding charges | bar: J
126 | Printing | Satchels - Decide on style |  | Jun | [21 empty] | Shoulder strap, size, quality, suitability for logos | bar: J
127 | Printing | Satchels - Decide on logos to be shown |  | Jun | [21 empty] | Colour, embroided, printed? | bar: J
128 | Printing | Satchels - Decide on inserts |  | Jun | [21 empty] | CD's, Sponsor Material, Handbooks | bar: J
129 | M'gement | Apparel - Consider Uniforms, Host identification |  | Jun | [21 empty] | Staff identification | bar: J
130 | Transport | Travel - Educational off site - Arrange transport |  | Jul | [21 empty] | Review numbers close to event | bar: J
131 | Transport | Travel - Social off site - Arrange transport |  | Jul | [21 empty] | Review numbers close to event | bar: J
132 | Educ. Prog. | VIP Presenters - Review protocols |  | Jul | [21 empty] | Meet & greet, introductions, security | bar: J
133 | Social Prog. | Printing needs - Decide on requirements |  | Jul | [21 empty] | Tickets, Menus, Place Cards, Invitations, Signs | bar: J
134 | Printing | Name Badges - Decide on requirements |  | Jul | [21 empty] | Format, colours, style, pouches, lanyards | bar: J
135 | M'gement | Delegate surveys - Decide on content |  | Jul | [21 empty] | Incentive prize | bar: J
136 | Spon'ship. | Sponsor surveys - Decide on content |  | Jul | [21 empty] | Personal interviews | bar: J
137 | Educ. Prog. | Presenters - Contact all re CV's, AV, abstracts, registration |  | Jul | [21 empty] | Mail or email of acceptance or not, contracts | bar: J
138 | Educ. Prog. | Poster presenters - Contact re displays |  | Jul | [21 empty] | Set up, location, times | bar: J
139 | Educ. Prog. | Structure - Finalise format |  | Jul | [21 empty] | Meeting rooms required, times, layouts | bar: J
140 | Educ. Prog. | Chairpersons - Select & confirm availability |  | Jul | [21 empty] | Select on ability to Chair | bar: J
141 | M'gement | Staffing requirements - Decide on roles & times |  | Jul | [21 empty] | Location, responsibilities, hours | bar: J
142 | Transport | Travel requirements - Arrange travel for Support Staff |  | Jul | [21 empty] | Management, Registration, Audiovisual | bar: J
143 | Merch'dise | Presenters' gifts - Decide |  | Jul | [21 empty] | Different style for internationals | bar: J
144 | Printing | Certificates - Presenters, Sponsors, Committee |  | Jul | [21 empty] | Decide when presented | bar: J
145 | Merch'dise | Satchels - Place order |  | Aug | [21 empty] | Logos & text reqd. | bar: A
146 | Spon'ship. | Floorplan - Review & finalise with Venue & Contractor |  | Aug | [21 empty] | Check for late orders | bar: A
147 | Spon'ship. | Exhibitor Manual - Prepare |  | Aug | [21 empty] | Deliveries, storage, trolleys, set up time, OHS, returns | bar: A
148 | Spon'ship. | Floorplan - Review with Venue, Exhibition Contractor |  | Aug | [21 empty] | Review for any changes | bar: A
149 | Spon'ship. | Sponsor & Exhibitor entitlements - Review |  | Aug | [21 empty] | Ensure contracted benefits can be delivered | bar: A
150 | Spon'ship. | Sponsor & Exhibitor Satchel Inserts |  | Aug | [21 empty] | Arrange for satchel inserts to be sent to you | bar: A
151 | Promotion | Media - Distribute media kits |  | Aug | [21 empty] | Mail, CD | bar: A
152 | Promotion | Media - Decide on interviews |  | Aug | [21 empty] | People, approval, times | bar: A
153 | Educ. Prog. | Presenters - Collate CV's for Introductions by Chairpersons |  | Aug | [21 empty] | Introduction is usually more personal than a CV | bar: A
154 | Transport | Travel requirements - Arrange Airport Transfers |  | Aug | [21 empty] | Presenters, VIP's, delegates | bar: A
155 | Venue | Staging - Review stage size, room layouts |  | Aug | [21 empty] | Heights, lecterns, floorplans | bar: A
156 | M'gement | Event Order - Prepare draft & review |  | Aug | [21 empty] | Review with Venues, Audiovisual, Contractors | bar: A
157 | Social Prog. | Running Order - Prepare |  | Aug | [21 empty] | Details of what, who & when | bar: A
158 | Transport | Travel requirements - Arrange local transport to Venues |  | Aug | [21 empty] | To & from off site venues | bar: A
159 | Promotion | Media Release - Arrange |  | Aug | [21 empty] | Has host already have a media outlet? | bar: A
160 | Accom. | Room blocks - Review utilisation with Venues |  | Aug | [21 empty] | Ensure client is not liable for unsold rooms | bar: A
161 | Accom. | Room blocks - Release unwanted rooms |  | Aug | [21 empty] | Check for any penalties | bar: A
162 | Venue | Catering - Review menus |  | Aug | [21 empty] | Day time, functions, off site food & beverages | bar: A
163 | Educ. Prog. | Papers - Receive Full Papers from accepted Presenters |  | Aug | [21 empty] | If required | bar: A
164 | Printing | Papers - Arrange publication of Papers |  | Aug | [21 empty] | CD or printed or on web site | bar: A
165 | Printing | Handbook - Prepare draft with Abstracts or Papers |  | Aug | [21 empty] | Collect Sponsors' profiles | bar: A
166 | Printing | Conference Handbook - Prepare content |  | Aug | [21 empty] | Abstracts, papers, workshops, program, floorplan | bar: A
167 | Social Prog. | Entertainment - Review |  | Aug | [21 empty] | Change rooms, band meals | bar: A
168 | Staging | Running sheet - Prepare detailed requirements |  | Aug | [21 empty] | Final schedule for AV company, review needs & costs | bar: A
169 | Educ. Prog. | Presenters & chairpersons’ meeting - Arrange |  | Aug | [21 empty] | Usually day before conference; Review AV, introductions | bar: A
170 | Venue | Signs - Decide on requirements |  | Aug | [21 empty] | Directional, hosts, costs, placement, positioning | bar: A
171 | Venue | Registration Desk - Decide on requirements |  | Aug | [21 empty] | Location, hours, signs, flowers, panelling, computing, phones | bar: A
172 | Venue | Presenters Preparation Room - Decide on requirements |  | Aug | [21 empty] | Furniture, catering, audiovisual, security | bar: A
173 | Venue | Security - Decide on requirements |  | Aug | [21 empty] | Hours, location, costs | bar: A
174 | Venue | Media Room - Decide on requirements |  | Aug | [21 empty] | Furniture, catering, audiovisual, security | bar: A
175 | Venue | Committee Room - Decide on requirements |  | Aug | [21 empty] | Furniture, catering, audiovisual, security | bar: A
176 | Merch'dise | Satchel packing - Plan process |  | Aug | [21 empty] | Collate all materials, pack & store | bar: A
177 | Merch'dise | Presenters' gifts - Arrange |  | Aug | [21 empty] | Review numbers | bar: A
178 | Finance | Insurance - Review all Contractors' Insurance |  | Aug | [21 empty] | AV, Transport, operators, entertainers | bar: A
179 | Venue | Medical - Review First Aid procedures, contacts |  | Aug | [21 empty] | All venues | bar: A
180 | Transport | Travel requirements - Educational - Review transport |  | Sep | [21 empty] | Check numbers, coaches, hosts | bar: S
181 | Transport | Travel requirements - Social - Review transport |  | Sep | [21 empty] | Check numbers, coaches, venues | bar: S
182 | Educ. Prog. | Chairpersons' - Prepare brief & distribute |  | Sep | [21 empty] | Notes to advise Chairpersons | bar: S
183 | Social Prog. | Review all bookings |  | Sep | [21 empty] | Confirm numbers, check contracts | bar: S
184 | Venue | Special diets - Supply for catering |  | Sep | [21 empty] | Main venue & off site venues | bar: S
185 | Accom. | Deposits - Send bookings to Venues |  | Sep | [21 empty] | Deposits, Special needs, VIP's, upgrades | bar: S
186 | Spon'ship. | Exhibitor Manual - Distribute |  | Sep | [21 empty] | Final floorplan, bump in & out schedule | bar: S
187 | Aud'visual | Requirements - Review quote |  | Sep | [21 empty] | Once Presenters needs are known | bar: S
188 | Educ. Prog. | VIP's - Review procedures & protocol |  | Sep | [21 empty] | Transport, greeting | bar: S
189 | M'gement | Photography - Decide on requirements |  | Sep | [21 empty] | Costs, copyright, publication, conference video | bar: S
190 | M'gement | Photography - Brief Photographer |  | Sep | [21 empty] | VIP's, times, use of photos, copyright | bar: S
191 | Printing | Conference Handbook - Print |  | Sep | [21 empty] | Check quantity | bar: S
192 | M'gement | Computing - Review on site needs |  | Sep | [21 empty] | Photocopying, faxes, www access, lighting | bar: S
193 | Transport | Tour arrangements - Review |  | Sep | [21 empty] | Check numbers, coaches, hosts | bar: S
194 | On Site | Display materials for delegates - Prepare |  | Sep | [21 empty] | Delegate list, maps, admin. info., program on display | bar: S
195 | Aud'visual | Sponsor slides - Prepare |  | Sep | [21 empty] | Acknowledgement of their contribution - shown at start | bar: S
196 | M'gement | Event Order - Finalise detail |  | Sep | [21 empty] | Required for major review with Venue | bar: S
197 | M'gement | Staff Briefing - Prepare brief |  | Sep | [21 empty] | Roles, venue facilities, procedures, room monitors | bar: S
198 | Aud'visual | Review AV requirements - Send to AV company |  | Sep | [21 empty] | Latest Presenter requirements | bar: S
199 | Aud'visual | Conference slides - Prepare |  | Sep | [21 empty] | PowerPoint, videos | bar: S
200 | Aud'visual | Presenter & Program slides - Prepare |  | Sep | [21 empty] | PowerPoint, videos | bar: S
201 | Venue | Catering - Review final numbers |  | Sep | [21 empty] | All venues | bar: S
202 | Transport | Coach capacities - Review final numbers |  | Sep | bar: S
203 | Finance | Insurance Cover - Review policy against final numbers |  | Sep | [21 empty] | Ensure cover is adequate if orig. situation changed | bar: S
204 | M'gement | Risk Policy - Review plans |  | Sep | [21 empty] | Has risk changed? | bar: S
205 | Social Prog. | Running Sheet - Review |  | Oct | [21 empty] | Ensure all roles & times are understood | bar: O
206 | Printing | Name Badges - Print & assemble |  | Oct | [21 empty] | Tickets to be included in pouches? | bar: O
207 | On Site | Ceremonies - Rehearsal |  | Oct | [21 empty] | Consider rehearsal for major program segments & social | bar: O
208 | On Site | Chairpersons' & Presenters Meeting |  | Oct | [21 empty] | Helpful to avoid problems | bar: O
209 | On Site | Staffing - Brief all helpers on roles at the conference |  | Oct | [21 empty] | All casual staff & committee briefed to assist delegates | bar: O
210 | Finance | Debt collection |  | Oct | [21 empty] | Ensure debts are collected before conference | bar: O
211 | On Site | Meetings - Final review - Venue, Contractors, AV, Committee |  | Oct | [21 empty] | Day prior, check final program | bar: O
212 | On Site | Returns - Material left behind, lost property |  | Oct | [21 empty] | Check & decide on return | bar: O
213 | M'gement | Thank you letters to Presenters & sponsors |  | Nov | [21 empty] | Personalised, signed by client | bar: N
214 | M'gement | Delegate surveys - Collate |  | Nov | [21 empty] | Publish outcomes? | bar: N
215 | Spon'ship. | Sponsor surveys - Collate |  | Nov | [21 empty] | May include phone follow up | bar: N
216 | Finance | Financial report - Finalise |  | Dec | [21 empty] | Profit & Loss required | bar: D
217 | M'gement | Measure realisation of goals |  | Dec | [21 empty] | Measure of event success | bar: D
218 | M'gement | Event report - Finalise |  | Dec | [21 empty] | Committee contributions required | bar: D
219 | M'gement | Committee - Celebration meeting |  | Dec | [21 empty] | Reward for job well done | bar: D
Note on B1: Example is based on starting in April for an Association conference in mid October the following year. Refer to the "Notes on Worksheet".
Note on C12: It is very helpful to determine how long tasks will take in hours. This will help you to see if you have adequate people resources to complete all tasks on time.
Note on D3: Please read the Notes on the Worksheet by opening the other Worksheet (bottom left).
Note on D13: Insert the initials of the person responsible in this column.
Note on E17: These are the dates when the task needs to be completed. Insert the day & month in this column.
Note on G22: Insert the day of the month in this column.
Note on K35: All comments can be printed by selecting Page Set Up, Sheet then Comments.