## AV Equipment
AV Equipment Bid List
Meeting | 21st Interantional Conference on XYZ | [5 empty] | Delivery |  | 5/15, 2pm
Dates | 16-23 May 20XX | [5 empty] | Pickup |  | 5/22 (final pickup on 5/23)
Location | Los Angeles Airport Marriott
Bid Company | [6 empty] | Company: |  | Corbin Ball Associates
Bid Contact | [6 empty] | Contact: |  | Corbin Ball, CMP
Phone | [6 empty] | Phone |  | 360.734.8756
Fax | [6 empty] | Fax: |  | 360.734.2204
Email | [6 empty] | Email: |  | corbin@corbinball.com
| Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Unit Total | Unit Cost | Total Cost
| 2012-05-16 | 2012-05-17 | 2012-05-18 | 2012-05-19 | 2012-05-20 | 2012-05-21 | 2012-05-22 | 2012-05-23
Data Projector , 3,000 lumens | 1 | 15 | 12 | 8 | 8 | 8 | 2 | 1 | 15 | 200 | 3000
Back-up overhead projector |  | 2 | 2 | 2 | 1 | 1 |  |  | 2 | 85 | 170
Slide Projector w/spare lamp, remote adv.* |  | 1 | 1 | 2 | 2 | 2 |  |  | 3 | 75 | 225
lenses (4-8") with rack for above |  | 1 | 1 | 2 | 2 | 2 |  |  | 3 | 55 | 165
Caramates for Preview Station | [8 empty] | 2 | 215 | 430 | bar: 2012-05-17 to 2012-05-21
Carousel Trays |  | 10 | 10 | 10 | 10 | 10 |  |  | 12 | 0 | 0
Safelock Stands |  | 2 | 2 | 2 | 1 | 1 |  |  | 3 | 45 | 135
Screens (12') | 2012-05-19: 2; 2012-05-20: 2; 2012-05-21: 2 | 2 | 465 | 930
Screens (8') w/ keystone eliminator | 1 | 7 | 7 | 7 | 7 | 7 | 2 | 1 | 7 | 85 | 595
Screens (6') w/ keystone eliminator | 1 | 8 | 8 | 1 | 1 | 1 |  |  | 8 | 75 | 600
Lectern Mic with cable* | 2012-05-20: 6; 2012-05-21: 2 | 9 | 55 | 495
Lapel Mic with cable* | 2012-05-19: 4; 2012-05-20: 4; 2012-05-21: 4 | 5 | 55 | 275
Wireless audience mic with batteries | 2012-05-19: 2; 2012-05-20: 2; 2012-05-21: 2 | 3 | 325 | 975
Table mics with stands | 2012-05-19: 2; 2012-05-20: 2; 2012-05-21: 2 | 3 | 55 | 165
standing mic (in exhibit hall) | [8 empty] | 2 | 55 | 110 | bar: 2012-05-18 to 2012-05-20
mixer (4 channel XL input) | [8 empty] | 2 | 75 | 150 | bar: 2012-05-19 to 2012-05-21
DVD/Bluray Player | [8 empty] | 1 | 100 | 100 | bar: 2012-05-17 to 2012-05-21
Overhead projector | [8 empty] | 2 | 25 | 50 | bar: 2012-05-19 to 2012-05-21
LCD or DLP projectors - InFocus 725 - 750 ANSI Lumens, 800x600 |  |  |  | 3 | 3 | 3 | 1 | 1 | 3 | 995 | 2985
Cart (42") w/skirting for video Projection | 2012-05-19: 4; 2012-05-20: 4; 2012-05-21: 4 | 4 | 55 | 220
White board | 2012-05-17: 8; 2012-05-18: 8 | 8 | 85 | 680
Flip Chart w/markers/ pads | [8 empty] | 7 | 55 | 385 | bar: 2012-05-17 to 2012-05-23
AC cords | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 0 | 0
AC power strips | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 0 | 0
Total | [10 empty] | 12840
Discount | 2012-05-16: 50% |  |  | 6420
Discount Equipment Total w/o tax | [10 empty] | 6420
Sales Tax | 2012-05-16: 8.25% |  |  | 529.65
Equipment Total | [10 empty] | 6949.65
Estimated Labor Charges - No Charge For Delivery | [10 empty] | 2500
Grand Total | [10 empty] | 9449.65
AV Equipment Bid Worksheet
This worksheet provides a bid sheet that can be emailed to AV companies. It computes the total daily unit total for equipment from the day-by-day totals entered. A unit cost can then be assigned by the AV company, and automatically calculating a total cost per equipment type.
The sheet provides cells for discounts to be inserted, as well as for sales tax, labor, and delivery charges. The total cost is found at the bottom.