## Sheet1
Calendar for XYZ Meeting
Meeting date | 2015-05-09 | Task | Person in Charge
One year | 2014-05-09 | Summarize results of overall and individual session surveys from previous meeting
6 months | 2014-11-10 | Contact office contacts and prepare attendee list. Create group mailing list for email
6 months | 2014-11-10 | Site visit to resort.
5 months | 2014-12-10 | Survey attendees for topic ideas and interest
5 months | 2014-12-10 | Prepare preliminary agenda and events. Send to coordinator.
4 months | 2015-01-09 | Compile list of topics and make session recommendations to Session Chair (SC)
4 months | 2015-01-09 | Get SC approval for topics, agenda, events.
4 months | 2015-01-09 | Confirm activities and events.
3 months | 2015-02-08 | Confirm session chairs and request session descriptions
3 months | 2015-02-08 | Contact outside speakers and confirm dates, fee and expense arrangements.
3 months | 2015-02-08 | Prepare final agenda, sessions and descriptions
3 months | 2015-02-08 | Develop signup database.
3 months | 2015-02-08 | Office staff conference call to discuss meeting and schedule.
2 months | 2015-03-10 | Send registration database to attendees.
2 months | 2015-03-10 | Design program and collateral materials.
2 months | 2015-03-10 | Send message to speakers regarding handouts and AV requests.
1 month | 2015-04-09 | Confirm all meeting space and meal locations for program.
1 month | 2015-04-09 | Develop session survey forms to include in program. Overall session evaluation will be done on Notes.
1 month | 2015-04-09 | Develop archive and survey database.
1 month | 2015-04-09 | Send attendee list and agenda to Communications to make signs and nametags.
3 weeks | 2015-04-18 | Request travel information.
3 weeks | 2015-04-18 | Send all banquet and event orders, meeting resume and flight manifest to hotel and DMC.
1 week | 2015-05-02 | Ship supplies, programs, nametags, signs, handouts to hotel.
Post meeting |  | Review evaluations and write meeting summary.
Post meeting |  | Prepare estimate budget for meeting.
Post meeting |  | Review final costs and prepare budget report for SC.
This automated calendar allow you to enter a date (cell B3 -- the red date) and it will automatically calculate the deadline dates leading up to it. Note: simple numerical date formatting can be entered (5/9/15 for May 9, 2015).
Thanks to Lisa Shimuzu, Corporate Meeting Planner for Milliman & Roberston, Inc., who contributed this sheet.